## ProductBackLog
Project Name: Bes(t)poke Group Members:Berk Mertoğlu, Atakan Coşar, Zeynep Durmuş, Aslı ARAS, Ata Barış Kuğu, Berkay KOÇ, Eralp Çolakoğlu, Arzum Naz Güney
# | Product BackLog
1 | Database Planning
2 | Allow users to sign up and log in.
3 | Allow users to create public profiles featuring portfolios, pricing, and mandatory expertise tags.
4 | Enable clients to browse through creator profiles.
5 | Enable users to search for creators and filter by price,tags etc.
6 | Let users create creator-defined order forms.
7 | Let users create creator-defined revision forms.
8 | Enable users to place orders.
9 | Enable users to demand revisions.
10 | Enable creators and clients to communicate through a in-app chat system.
11 | Enable users to apply adversarial noise processing (AI Shield) to portfolio items.
12 | Implement a credentials verifying system.
13 | Process payments securely using an escrow based payment provider.
14 | Track commisions, display commision history, and manage commision statuses.
15 | Create a two-way review and rating system.
16 | Create a report system.
17 | Provide administrative controls to manage accounts, disputes, and reports.
18 | Ensure the website is optimized for various devices with an engaging user interface.
19 | Implement a notification system.
20

## Sprint-1
SPRINT-1
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer, Product Owner | Database Planning | In Progress | High | 2028-09-03 | 2028-09-28 | 26 | A robust database is the central, structured repository that efficiently stores, organizes, and secures all critical application data.
Developer | User Registration and Authentication | Ready to Start | High | 2028-09-03 | 2028-09-11 | 9 | Sign-up/login with role selection.
Developer | User Profile Creation/Management | Ready to Start | High | 2028-09-11 | 2028-09-21 | 10 | Allow access to different permission sets according to the chosen role.
26
BACKLOG
As a user, I want to register with my email address with role selection, so that I can access my account.
STATUS: Ready to Start
As a user, I want to be able to edit my personal profile according to my role so I can clearly communicate my wants or sevices.
STATUS: Ready to Start
Dev
Dev

## Sprint-2
SPRINT-2
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer | Creator Portfolio Browsing | Not Started | High | 2028-10-01 | 2028-10-01 | 10 | Display items from the portfolio's of creators.
Developer | Creator Search & Filter | Not Started | Medium | 2028-10-10 | 2028-10-19 | 10 | Include keyword search; category,price etc. filter.
Developer | Custom Order Form Creation | Not Started | Medium | 2028-10-10 | 2028-10-16 | 7 | Creator-defined order forms with multiple field types(e.g., text input, multiple choice, checkbox, dropdown list, and file upload (max 20MB))
Developer | Custom Revision Form Creation | Not Started | Medium | 2028-10-16 | 2028-10-18 | 3 | Creator-defined revision forms with multiple field types(e.g., text input, multiple choice, checkbox, dropdown list, and file upload (max 20MB))
Developer | Commision Placement Functionality | Not Started | High | 2028-10-18 | 2028-10-24 | 7 | Allow users to fill the order forms(custom or default) and place their order.
Developer | Revision Demand Functionality | Not Started | High | 2028-10-24 | 2028-10-26 | 3 | Allow users to fill the revision forms(custom or default) and demand changes.
26
BACKLOG
As a user with client role, I want to search for creators by username or genre and filter them by category, so that I can find matching profiles easily.
STATUS: Not Started
As a creator, I want to create custom order/revision forms, so that I can guide unexprienced clients as they list their requirements.
STATUS: Not Started
Dev
As a user with client role, I want to see a list of available creators with basic information, so that I can quickly browse and find what I’m
looking for.
STATUS: Not Started
Dev
Dev
As a user with client role, I want to fill order forms provided by thesystem or creators, so that I can place my order.
STATUS: Not Started
Dev
As a user with client role, I want to fill the revision forms provided by the system or creators, so that I can demand changes to an ongoing commision.
STATUS: Not Started
Dev

## Sprint-3
SPRINT-3
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer | Chat System | Not Started | Medium | 2028-10-29 | 2028-11-05 | 8 | Allows for clear comminication between the client and the creator.
Developer | Adversarial Noise Processing Integration | Not Started | Low | 2028-10-29 | 2028-11-05 | 8 | AI Shield (e.g.,Glaze,Nightshade)
Developer | Verified Credentials System | Not Started | Low | 2028-11-05 | 2028-11-13 | 9 | Implementation of diploma upload API
Developer | Commision status tracking system | Not Started | High | 2028-11-05 | 2028-11-13 | 9 | Track commision status/history, revision count
Developer | Two-way Review & Rating System | Not Started | Medium | 2028-11-13 | 2028-11-18 | 6 | Both the clients and creators can post reviews and ratings after the comission process is finished.
Developer | Two-way Report System | Not Started | Medium | 2028-11-18 | 2028-11-23 | 6 | Both the clients and creators can post reviews and ratings after the comission process is finished.
26
BACKLOG
As a user, I want to direct message creators or clients I am in business with in the application , so that I can clerly communicate with them without giving personal contact information.
STATUS: Not Started
As a user with client role, I want to view my commision history and the current status of the commisions I ordered, so that I can track my purchases and know when ı will recieve the product.
STATUS: Not Started
Dev
Dev
As a user with creator role, I want apply AI shield to my portfolio item without using another program,so that I can upload my portfolio without fearing it will be stolen for unauthorised usage in AI generation.
STATUS: Not Started
Dev
As a user with creator role, I want to view my commision history and the current status of the commisions I recieved, so that I can track work history and know what projects are needed to be done.
STATUS: Not Started
Dev
As a user, want to rate and review other users I have worked with, so that I can share my exprience and personal opinion or report the user if necessary, and thus help other users.
STATUS: Not Started
Dev
As a user, I want portfolio items like certificates and diplomas to be verified, so that I can be able to trust the abilities of the creators.
STATUS: Not Started
Dev

## Sprint-4
SPRINT-4
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer | Escrow Based Payment Gateway Integration | Not Started | High | 2028-11-26 | 2028-12-05 | 10 | Secure payment processing(İyizico).
Developer | Creating Admin Panel | Not Started | Low | 2028-12-05 | 2028-12-14 | 10 | Manage accounts, disputes, and reports.
Developer | Responsive Design & UX Enhancements | Not Started | Medium | 2028-12-14 | 2028-12-21 | 8 | Ensure mobile-friendly layout, improved UX.
Developer | Notification System | Not Started | Low | 2028-12-14 | 2028-12-19 | 6 | Triggering alerts for new messages, order status updates, and payment confirmations. (Email/In-App)
26
BACKLOG
As a user, I want to perform money transactions safely by a trustable payment gateway, so that the exchange is securely done and I receive confirmation.
STATUS: Not Started
As an admin, I want to access a dashboard that lets me manage accounts, disputes, and reports, so that I can efficiently supervise the workflow and keep the operations running smoothly.
STATUS: Not Started
Dev
As a user, I want the application to be responsive and easy to use on multiple forms of devices like desktop, tablet, and phones, so that I can access it without problem from any device.
STATUS: Not Started
Dev
Dev
As an user, I want to recieve notification about commsion status, new orders and messages, so that I can respond effectively.
STATUS: Not Started
Dev

## KeyDropdowns
KEY DROPDOWNS - DO NOT DELETE
PRIORITY KEY | STATUS KEY
High | In Progress
Medium | Ready to Start
Low | Complete
On Hold
Testing
Not Started

## Templates
TEMPLATES
ASSIGNED TO | KANBAN CARDS
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here